## Schedule
ID | Workstream | Task | Status | Priority | Target Window | Dependencies | Deliverable / Output | Notes
GQ-001 | Foundation | Core validation engine established | Done | High | Completed 2026-03-18 |  | geoqa/validations/* | Base validation layer is in place.
GQ-002 | Foundation | Agent workflow established | Done | High | Completed 2026-03-18 | GQ-001 | geoqa/agent.py | Dataset routing, reporting, and conservative fixes exist.
GQ-003 | Foundation | Thermal safety layer hardened | Done | High | Completed 2026-03-18 |  | geoqa/thermal.py | Strict/cool/balanced profiles are present.
GQ-004 | Testing | Public-sample integration baseline | Done | High | Completed 2026-03-18 | GQ-001,GQ-002 | data/integration_results/ | Natural Earth and Philadelphia sample runs recorded.
GQ-005 | ML Prep | ML-ready QA annotation and export layer | Done | Medium | Completed 2026-03-18 | GQ-001 | geoqa/ml/* | QA outputs can be carried into ML pipelines.
GQ-006 | UI / Conversion | Vector conversion and Streamlit entry point | Done | Medium | Completed 2026-03-18 | GQ-001,GQ-003 | streamlit_app.py | Vector-first local UI exists.
GQ-007 | Onboarding | Quickstart onboarding assets | Done | Medium | Completed 2026-03-18 | GQ-001 | docs/start_here_guide.md; examples/geoqa_quickstart.ipynb | Low-friction first-run path added.
GQ-008 | Testing | Expand real-dataset integration coverage | Next | High | Next 1-2 weeks | GQ-004 | New profiles + recorded outputs | Cover more formats, schemas, and dataset types.
GQ-009 | Testing | Add more synthetic edge-case fixtures | Next | High | Next 1-2 weeks | GQ-004 | data/public_samples/edge_cases/ | Focus on CRS, geometry, and attribute anomalies.
GQ-010 | UI / Conversion | Add downloadable validation/fix reports in Streamlit | Next | High | Next 1-2 weeks | GQ-006 | Updated streamlit_app.py | Should stay lightweight and deterministic.
GQ-011 | Validation | Deepen validator quality on messy real-world data | Next | High | Next 2-4 weeks | GQ-008,GQ-009 | Improved validators + regression coverage | Focus on robustness, not just breadth.
GQ-012 | Fixes | Add more safe deterministic fix helpers | Next | Medium | Next 2-4 weeks | GQ-011 | Expanded geoqa/fixes.py | Only where behavior is predictable and auditable.
GQ-013 | Onboarding | Add more onboarding notebooks | Next | Medium | Next 2-4 weeks | GQ-007 | Additional notebooks | Suggested: agent workflow basics and ML-ready outputs.
GQ-014 | DevOps | Add CI for unit and lightweight checks | Next | Medium | Next 2-4 weeks | GQ-004 | CI workflow files | Keep checks lightweight for heat-sensitive local work.
GQ-015 | Packaging | Clarify packaging and installation flow | Next | Medium | Next 2-4 weeks | GQ-001 | Packaging metadata / install docs | Needed for broader adoption.
GQ-016 | Validation | Broaden topology validation depth | Later | Medium | Later | GQ-011 | Expanded topology validators | Deeper topology work should follow more field testing.
GQ-017 | Validation | Add dataset-specific validation packs | Later | Medium | Later | GQ-011 | New validation modules / packs | Build from real use cases rather than speculation.
GQ-018 | Testing | Add optional performance and stress-test runs | Later | Medium | Later | GQ-008,GQ-014 | Stress profiles + metrics | Keep opt-in because of thermal cost.
GQ-019 | UI / Review | Add richer visual before/after geometry review | Later | Low | Later | GQ-010,GQ-012 | Enhanced preview workflow | Useful, but not before core robustness work.
GQ-020 | Benchmarks | Add benchmark manifests for validated public datasets | Later | Low | Later | GQ-008 | Benchmark manifests + docs | Supports community reuse and comparisons.
GQ-021 | ML Prep | Expand ML feature engineering from QA outputs | Later | Low | Later | GQ-005 | Expanded geoqa/ml/features.py | Defer until baseline ML use cases are clearer.
GQ-022 | Raster | Consider raster support after dedicated layer exists | Later | Low | Later | GQ-015 | Raster processing layer | Do not over-claim raster support before implementation.

## Legend
GeoQA Project Schedule
Status | Meaning
Done | Implemented and documented.
Next | Highest-value near-term work.
Later | Useful future work after higher-priority items.
Reading Tips | Workstream and priority cells are color-coded; the schedule sheet is filtered and frozen for easier scanning.
Notes | This workbook is a management view derived from docs/checklist.md and plan_of_action.md.
Use checklist.md for quick text status and journal.md for detailed rationale/history. | Use checklist.md for quick text status and journal.md for detailed rationale/history.